## Self-hosted Checklist
Platform / Method | Powered by | Page | Flow | How to Test | Owner | Observations
SuprSend Platform | - | All | SuprSend Interface | - Check if interface is loading on your cluster
SuprSend Platform | - | Login | Login | - Check if you are able to login to SuprSend
SuprSend Platform | All | Invite User | Account Settings > Teams | - Check if the invite flow is working for your team member
SuprSend Platform | - | All | Main dashboard - left panel | - Check if all tabs are loading without error
SuprSend Platform | Hub | Workspace | Navbar > Add Workspace | - Create a new workspace - Do any activity (eg. API call or create template) to see if connection is working fine
SuprSend Platform | Backend | Vendors | Main dashboard - vendors | - Check if you are able to configure SMS and email vendors
SuprSend Platform | Hub | Templates | Create a new template | - Check if you are able to create and save dummy templates (email)
SuprSend Platform | Hub | Workflows | Create a new workflow | - Check if you are able to create and save a test workflow
SuprSend Platform | Hub | Users | Create a new user | - Check if you are able to create and save a test user
SuprSend Platform | Hub Clickhouse | Workflows | Workflow Detail Page > Test | - Trigger a test workflow with sample payload to a user - Check if requests are getting logged in `Request` tab - Check if workflow is successfully executed in `Executions` tab - Check messages tab (Notifications triggered to users will show up here. If your workflow had any delivery node, its log will be visible in messages tab)
SuprSend Platform | Clickhouse | Dashboard | Analytics | - Check if graphs are loading and showing relevant data
Rest API | Hub |  | Test 1 API call (eg. workflow trigger) | - Make any API call with your updated API endpoint and see if it's logged in Logs -> Request tab on SuprSend Interface
Management API | Backend |  | Test 1 API call (eg. list workflows) | - Make any API call with your updated API endpoint and see if you are getting results in the response
SuprSend Platform | Third Party Service | Add Webhook | Developers > Webhook | - Add webhook. Enable events and test if you are getting vendor response back to the webhook. - You'll have to also pass your hub endpoint inside vendor portal to get delivery status within SuprSend logs
SuprSend Platform | Hub | Schema | Developers > Schema | - Add new schema - Link it to a workflow - Trigger workflow via API with schema mismatch - Check if you are getting error in API response and requests logs on UI
SuprSend Platform | Backend | Account Settings | Audit logs | - check if data is populated
CLI | Backend |  |  | Test 1 command and see if it's working
Frontend SDK | SDK | Inbox | Integrate React SDK | Integrate with frontend SDK, send a test trigger to Inbox and see if sent notification is showing up in Inbox to test if the connection is successful
Frontend SDK | SDK | Preferences | Integrate React SDK | Integrate with frontend SDK, send a test trigger to Inbox and see if sent notification is showing up in Inbox to test if the connection is successful
MCP | Backend |  |  | Just check setup and 1 tool call
SuprSend Platform | Pronto Service | Lists (optional) | Create List - database sync (optional) | - This is an optional step, needed only if you'll be using this feature - Add any SQL connector, add SQL query to update user in list and do a dry run to check if the connection is working
SuprSend Platform | Third Party Service | Connectors (optional) | Segment (optional) | Add Connector and test if the data is flowing properly